## Front
[ LOGO ] |  | PAYMENT CERTIFICATE |  |  | Cert No. 02 15 May 2026
Infrastructure Upgrade · Lephadimisha Secondary School · Contract No. 4504207699
Certificate No. | 02
Assessment Date | 15 May 2026
Date of Certificate | 15 May 2026
Contract No. | 4504207699
Retention Free Amount | R 933,007.68
CONTRACT VALUE SUMMARY
Description |  |  |  | Value (R)
Original Contract Value |  |  |  | 4665038.38
Total Contract Amendments To Date |  |  |  | 0
Sub Total |  |  |  | 4665038.38
VAT at 15% |  |  |  | 699755.757
Total Contract Value (incl. VAT) |  |  |  | 5364794.137
PAYMENT DUE — CERTIFICATE NO. 02
Description |  |  |  | Amount (R)
Value of Work Done (Cumulative – Cert No. 02) |  |  |  | 1494584.878
Plus: Compensation Events |  |  |  | -
Plus: Material On Site |  |  |  | -
Total Value of Work Done |  |  |  | 1494584.878
Less: Retention |  |  |  | -
Sub Total |  |  |  | 1494584.878
Less: Previous Amount Due |  |  |  | 448781.025
Sub Total |  |  |  | 1045803.853
Plus: V.A.T. at 15% |  |  |  | 156870.578
TOTAL AMOUNT NOW CERTIFIED (incl. VAT) |  |  |  | 1202674.431
Note: 5% Retention not deducted — handled by Valterra GSS. Retention: R 52,290.19
AUTHORISATION
Project Manager | M. Susela |  | Signature: _________________________________ |  | Date: __________
Quantity Surveyor | M. Hachinavamwe |  | Signature: _________________________________ |  | Date: __________
Section Manager – Project Governance | S. Tsokalamtengo |  | Signature: _________________________________ |  | Date: __________
Senior Manager PMU | H. Sifeni |  | Signature: _________________________________ |  | Date: __________
NBI Quantity Surveyors (Pty) Ltd ¦ Rustenburg Platinum Mines (PTY) LTD, 144 Oxford St, Rosebank, 2196 ¦ Payment Certificate No. 02 ¦ 15 May 2026