## Front
[ LOGO ] |  | PAYMENT CERTIFICATE |  |  | Cert No. 02 15 May 2026
Infrastructure Upgrade of Lephadimisha Secondary School in Mogalakwena ¦ Contract No. 4504207699
Certificate No. | 02
Assessment Date | 15 May 2026
Date of Certificate | 15 May 2026
Contract No. | 4504207699
Retention Free Amount | R 933,007.68
CONTRACT VALUE SUMMARY
Description |  |  |  | Value (R)
Original Contract Value |  |  |  | 4665038.38
Total Contract Amendments To Date |  |  |  | 0
Sub Total |  |  |  | 4665038.38
VAT 15% |  |  |  | 699755.757
Total Contract Value (incl. VAT) |  |  |  | 5364794.137
PAYMENT DUE — CERTIFICATE NO. 02
Description |  |  |  | Amount (R)
Value of Work Done (Cumulative – Cert No. 02) |  |  |  | 1494584.878
Plus: Compensation Events |  |  |  | -
Plus: Material On Site |  |  |  | -
Total Value of Work Done |  |  |  | 1494584.878
Less: Retention |  |  |  | -
Sub Total |  |  |  | 1494584.878
Less: Previous Amount Due |  |  |  | 448781.025
Sub Total |  |  |  | 1045803.853
Plus: V.A.T. at 15% |  |  |  | 156870.578
TOTAL AMOUNT NOW CERTIFIED (incl. VAT) |  |  |  | 1202674.431
Note: 5% Retention not deducted — handled by Valterra GSS. Retention: R 52,290.19
AUTHORISATION
Project Manager | M. Susela |  | Signature: _________________________________ |  | Date: __________
Quantity Surveyor | M. Hachinavamwe |  | Signature: _________________________________ |  | Date: __________
Section Manager – Project Governance | S. Tsokalamtengo |  | Signature: _________________________________ |  | Date: __________
Senior Manager PMU | H. Sifeni |  | Signature: _________________________________ |  | Date: __________
NBI Quantity Surveyors (Pty) Ltd ¦ Rustenburg Platinum Mines (PTY) LTD, 144 Oxford Street, Rosebank, Melrose, 2196 ¦ Confidential — Payment Certificate No. 02 ¦ 15 May 2026

## Summary
[ LOGO ] | BILL OF QUANTITIES — SUMMARY OF SECTIONS |  |  |  | Cert No. 02 15 May 2026
Lephadimisha Secondary School — Infrastructure Upgrade ¦ Payment Certificate No. 02 ¦ 15 May 2026
SCHED | DESCRIPTION | TENDER AMOUNT (R) | CUMULATIVE CERTIFIED (R) | PREVIOUS CERTIFIED (R) | AMOUNT DUE (R)
Section 1 | PRELIMINARY & GENERAL | 665333.14 | 447643.049 | 280455.025 | 167188.025
Bill No. 1 | Fixed Charge Items | 163267 | 113267 | 113267 | 0
Bill No. 2 | Time Related Items | 502066.14 | 334376.049 | 167188.025 | 167188.025
Section 2 | MEDIA CENTRE / LIBRARY | 428145 | 78300 | 0 | 78300
Bill No. 1 | Concrete | 35385 | 0 | 0 | 0
Bill No. 2 | Carpentry and Joinery | 254600 | 78300 | 0 | 78300
Bill No. 3 | Ironmongery | 100160 | 0 | 0 | 0
Bill No. 4 | Electrical | 5000 | 0 | 0 | 0
Bill No. 5 | Provisional Sums | 33000 | 0 | 0 | 0
Section 3 | ADMINISTRATION BLOCK | 1085624.7 | 611340 | 0 | 570453
Bill No. 1 | Concrete | 35385 | 0 | 0 | 0
Bill No. 2 | Carpentry and Joinery | 45000 | 0 | 0 | 0
Bill No. 3 | Ironmongery | 28440 | 0 | 0 | 0
Bill No. 4 | Plumbing and Drainage | 33250 | 29550 | 0 | 29550
Bill No. 5 | Electrical | 24800 | 19800 | 0 | 19800
Bill No. 6 | Provisional Sums | 918749.7 | 561990 | 0 | 521103
Section 4 | 3 CLASSROOM BLOCK + HOD OFFICE (G) | 1788987.2 | 647611.845 | 168326 | 479285.845
Bill No. 1 | Earthworks | 149046 | 149046 | 71586 | 77460
Bill No. 2 | Concrete | 307835 | 249995 | 96740 | 153255
Bill No. 3 | Masonry | 216908 | 182468 | 0 | 182468
Bill No. 4 | Waterproofing | 21040 | 17600 | 0 | 17600
Bill No. 5 | Roof Covering and Cladding | 82880 | 0 | 0 | 0
Bill No. 6 | Carpentry and Joinery | 36250 | 0 | 0 | 0
Bill No. 7 | Ceilings and Partitions | 102000 | 0 | 0 | 0
Bill No. 8 | Floor Coverings | 123050 | 0 | 0 | 0
Bill No. 9 | Ironmongery | 69180 | 0 | 0 | 0
Bill No. 10 | Structural Steelwork | 55860 | 0 | 0 | 0
Bill No. 11 | Metalwork | 44500 | 18500 | 0 | 18500
Bill No. 12 | Plastering | 66103 | 0 | 0 | 0
Bill No. 13 | Plumbing and Drainage | 32505 | 0 | 0 | 0
Bill No. 14 | Glazing | 18000 | 0 | 0 | 0
Bill No. 15 | Paint Work | 60546 | 0 | 0 | 0
Bill No. 16 | Electrical Installations | 113784.2 | 30002.845 | 0 | 30002.845
Bill No. 17 | Loose Furniture | 289500 | 0 | 0 | 0
Section 5 | 2 CLASSROOM BLOCK + HOD OFFICE (H) | 696948.34 | 199358.008 | 0 | 199358.008
Bill No. 1 | Concrete | 43040 | 0 | 0 | 0
Bill No. 2 | Carpentry and Joinery | 28280 | 0 | 0 | 0
Bill No. 3 | Ceilings and Partitions | 69500 | 69500 | 0 | 69500
Bill No. 4 | Floor Coverings | 88275 | 0 | 0 | 0
Bill No. 5 | Ironmongery | 54094 | 0 | 0 | 0
Bill No. 6 | Metalwork | 19500 | 0 | 0 | 0
Bill No. 7 | Plumbing and Drainage | 26735 | 0 | 0 | 0
Bill No. 8 | Glazing | 13500 | 13500 | 0 | 13500
Bill No. 9 | Paint Work | 50013 | 39480 | 0 | 39480
Bill No. 10 | Electrical Installations | 107611.34 | 76878.008 | 0 | 76878.008
Bill No. 11 | Loose Furniture | 196400 | 0 | 0 | 0
| TOTAL EXCLUDING VAT | 4665038.38 | 1984252.903 | 448781.025 | 1494584.878
| COMPENSATION EVENTS | 0 | 0 | 0 | 0
| MATERIAL ON SITE | 0 | 0 | 0 | 0
| GRAND TOTAL | 4665038.38 | 1984252.903 | 448781.025 | 1494584.878
| RETENTION ACCOUNT | 466503.838 | 198425.29 | 44878.102 | 74729.244
NBI Quantity Surveyors (Pty) Ltd ¦ Rustenburg Platinum Mines (PTY) LTD, 144 Oxford Street, Rosebank, Melrose, 2196 ¦ Confidential — Payment Certificate No. 02 ¦ 15 May 2026

## Media Centre
[ LOGO ] | SECTION 2 — MEDIA CENTRE / LIBRARY | [7 empty] | Cert No. 02 15 May 2026
Lephadimisha Secondary School ¦ Payment Certificate No. 02 ¦ 15 May 2026
ITEM | PAY REF | DESCRIPTION | UNIT | TENDER QTY | RATE (R) | TENDER AMT (R) | CUMUL. CERT (R) | PREV. CERT (R) | AMOUNT DUE (R)
BILL NO. 1 — CONCRETE (STRUCTURAL) | [6 empty] | 35385
SANS 1200G HIGH-TENSILE WELDED MESH
A |  | Ref 395 layer mesh in apron | m² | 67 | 135 | 9045
8.4 CONCRETE — Reinforced 25MPa/19mm
B |  | In apron | m³ | 10 | 2500 | 25000
8.4.4.c) WOODEN-FLOATED FINISH
C |  | Top Apron | m² | 67 | 20 | 1340
Carried to Summary — Bill No. 1 | [6 empty] | 35385
BILL NO. 2 — CARPENTRY AND JOINERY | [6 empty] | 254600 | 78300 | 78300
EAVES, VERGES ETC.
A |  | 250×10mm FC77 fibre cement fascias and barge boards | m | 60 | 125 | 7500
WORKTOPS
B |  | Worktop 1545×1350, 750mm wide, chromed legs, complete | No | 9 | 4500 | 40500
C |  | Worktop with shelves 1545×1350, 650mm wide, chromed legs, complete | No | 6 | 4500 | 27000 | 13500 |  | 13500
D |  | Fixed shelving 1545×2700, 750mm wide, chromed legs, complete | No | 6 | 4500 | 27000 | 13500 |  | 13500
E |  | Wall shelving 2400×1500mm high | No | 4 | 5000 | 20000
OFFICE TABLE AND CHAIRS
F |  | 120cm round desk | No | 6 | 5000 | 30000
G |  | Classic Ultra Exec Mid-Back Chair | No | 36 | 2850 | 102600 | 51300 |  | 51300
Carried to Summary — Bill No. 2 | [6 empty] | 254600 | 78300 | 78300
BILL NO. 3 — IRONMONGERY | [6 empty] | 100160
DOOR STOP
A |  | Half Moon Satin Nickel Door Stopper | No | 3 | 120 | 360
SHELVES
B |  | 2209×914×2438mm 5-tier powder coated wall bands, melamine shelves | No | 10 | 5500 | 55000
C |  | Magazines and Newspapers Steel Cabinet | No | 7 | 4200 | 29400
DESK
D |  | 800×1800×700 Mediterranean desk, 3-drawer pedestal with 'L' extension | No | 1 | 12500 | 12500
OFFICE CHAIR
E |  | Everfurn Office & Computer Chair: Mid Back ¦ Swift - Black | No | 1 | 2900 | 2900
Carried to Summary — Bill No. 3 | [6 empty] | 100160
BILL NO. 4 — ELECTRICAL INSTALLATIONS | [6 empty] | 5000
TESTING AND COMMISSIONING
A |  | Testing and commissioning of complete electrical installation (DB CoC) | Item | 1 | 5000 | 5000
Carried to Summary — Bill No. 4 | [6 empty] | 5000
BILL NO. 5 — PROVISIONAL SUMS | [6 empty] | 33000
FIRE EQUIPMENT
A |  | Provisional sum — supply and installation of fire equipment | Item | 1 | 10000 | 10000
B |  | Allow for attendance | % | 0.05 | 10000 | 500
C |  | Allow for profit | % | 0.05 | 10000 | 500
SIGNAGE
D |  | Door letters, name plates and rectangular sign boards | Item | 1 | 5000 | 5000
E |  | Allow for attendance | % | 0.05 | 5000 | 250
F |  | Allow for profit | % | 0.05 | 5000 | 250
ROCK / LANDSCAPING
G |  | Media centre rock landscaping | Item | 1 | 15000 | 15000
H |  | Allow for attendance | % | 0.05 | 15000 | 750
J |  | Allow for profit | % | 0.05 | 15000 | 750
Carried to Summary — Bill No. 5 | [6 empty] | 33000
SECTION 2 TOTAL — MEDIA CENTRE / LIBRARY | [6 empty] | 428145 | 78300 | 78300
NBI Quantity Surveyors (Pty) Ltd ¦ Rustenburg Platinum Mines (PTY) LTD, 144 Oxford Street, Rosebank, Melrose, 2196 ¦ Confidential — Payment Certificate No. 02 ¦ 15 May 2026